3 June 2010 ADD Team Conference Call Summary

Agencies Represented: CIRA, DTC, EMC, ESRL, HRD, NESDIS, NHC, NRL, TCMT

DISCUSSION

1. Bi-weekly calls

Bi-weekly meetings of the ADD will be held to improve coordination and communication. These will be held at 2 PM eastern time every other Wednesday on the weeks when there is no HFIP call led by Bob Gall. To get in phase with that, the next meeting will be June 9th, which will replace the ADD call previous scheduled for June 14th. The topics will alternate between products and diagnostics. The next meeting will emphasize products.

2. Summary of 5/24 call

A subset of the ADD team met on May 24 to discuss products. Three products were chosen for initial emphasis in FY10. These include a model shear product, a model cross-section product, and statistical intensity forecasts run from an ensemble of global models.

3. Proposed basic diagnostic file

Brian McNoldy is generating a simple ASCII large-scale diagnostic file (HFIP-lsdiag file) for the 2010 real time runs of the GFDL and HWRF. The diagnostics are based on what is used for the SHIPS and LGEM intensity forecast statistical models. Kate Musgrave is working on a program to run SHIPS/LGEM from this diagnostics file and some supplementary input from the ATCF A-Deck. It is proposed that similar files be produced from as many of the real time and HFIP demo models as possible. Mike Fiorino is working on the generation of these from the FIM, GFS, UKMET, ECMWF, NOGAPS and Canadian global models. HRD may produce these for HWRFx and NRL is considering producing these for COAMPS-TC. A file naming convention is needed, which will follow that developed by TCMT for the tier 1 and tier 2 datasets. TCMT might also serve as a central location for storing and distributing these files. In addition to running statistical models the HFIP-lsdiag files can be used to compare environmental fields between models.

4. Plans for synthetic satellite imagery

EMC is generating synthetic GOES channel 2, 3, 4 and 5 brightness temperatures from HWRF and GFS. For HWRF these already appear in the operational grib files. Plots of the HWRF synthetic imagery are being displayed using grads for HWRF on the HWRF web page. These can be improved by using more standard satellite-based color tables. CIRA is producing some suggested color tables for distribution to the ADD team. EMC plans to add the GFS synthetic imagery to their web page. NHC suggested a tropical strip (or maybe two strips) from roughly 0 to 50 deg N and from 0 to somewhere between 140 and 180 deg W for the GFS data.

CIRA also has the capability to generate McIDAS AREA files from the HWRF grib files. A test will be performed on the next TC to determine if CIRA and automatically produce the files and NHC can access them via ftp.

The capabilities to create synthetic IR imagery for HWRFx and COAMPS-TC are also being developed. NRL will work with CIRA to adapt their IR forward model. The HRD IR forward model is to be determined. The goal for next year is to also develop capabilities for microwave imagery. Both EMC and HRD will be working on this.

ACTION ITEMS

1. Ed Rappaport and Mark DeMaria will decide on a distribution list for the bi-weekly calls.

2. Louisa Nance will send Mark DeMaria the tier1 and 2 naming convention (completed)

3. Mark DeMaria will adapt the above naming to the HFIP-lsdiag files and send the information to the team.

4. Brian McNoldy will answer questions regarding the format of the diagnostic files.

5. Mark DeMaria will send the McIDAS color tables for GOES channels 2-5 to the team.

6. Mike Fiorino will share information with EMC and HRD on how to expand beyond 16 colors in grads.

7. CIRA will test the possibility of automating the generation of McIDAS AREA files from the HWRF synthetic satellite data.