ADD Team Conference Call Minutes (Thu 24 June 2010, 2-3 PM EDT)

Attendees:  Ed Rappaport, James Franklin, Wallace Hogsett, Janna O’Connor, Mike Fiorino, Mark DeMaria, John Knaff, Brian McNoldy, Kate Musgrave, Yi Jin, Ann Schrader, Buck Sampson

AGENDA ITEMS

1. Status of Simulated Imagery

Simulate IR imagery from HWRF and GFS are now routinely being generated by EMC and displayed on the HWRF web page using the color tables supplied by CIRA. The brightness temperatures are included in the grib files. Mark mentioned that a small adjustment to the color table might be needed. Janna said that would be straightforward to do. She also said it is okay to share the web page password with the ADD group and hurricane forecasters. The next step is to let the NHC forecasts know these are available and request feedback. Mike is also going to create images in real time and display them on the web. Also, Mark said he would generate all four simulated GOES IR channels using McIDAS and also create similar loops of real GOES data for the Hurricane Ike example.

Actions Needed:

a. Mark will send a message to the NHC hurricane specialist list request feedback on the satellite images.

b. Mark will create the real and simulated images for the Hurricane Ike example.

c. Janna will adjust the color table for the HWRF plots as needed.

2. Sample diagnostic file

Brian developed a simple ASCII diagnostic file and documentation. An example was sent to the ADD group. He is routinely creating these in real time for HWRF and GFDL. These are available from

http://einstein.atmos.colostate.edu/~mcnoldy/tropics/hwrf/2010

for HWRF with an analogous directory for GFDL. There was some discussion of making these available at a central location at the DTC, similar to the tier 1 and tier 2 data. The files can used for model evaluation and inter-comparison.

Actions Needed:

Consult with the DTC on the next ADD call to develop a plan for sharing the ASCII diagnostic  files.

3. Status of diagnostic file generation for global models

Mike is working on creating the ASCII diagnostic files for GFS, ECMWF, UkMet, Candian, NOGAPS and FIM global models. He will compare results with Brian on a GFS test case. These should be ready in a week or two.

4. Possibility of diagnostic files for HWRFx and COAMPS-TC

Yi said she will try to generate the diagnostic files for COMAPS-TC. HRD was not represented on the call, so no information was obtained about HWRFx.

Actions Needed:

Consult with HRD on the next call about HWRFx diagnostic files.

5. “Portable” version of SHIPS/LGEM

Kate is continuing development of a version of SHIPS/LGEM that can run off of the ASCII diagnostic files. She should have a preliminary version ready in about 2 weeks.

6. Other ensemble products

Mike is continuing development of ensemble based products, with emphasis on combining track and intensity information. Kate is working on combining ensemble products with the NHC wind probability model. That application will probably not be ready for testing in 2010.

Actions Needed:

Mike will let the group know when he wants feedback on the ensemble products.

7. Vertical cross sections in N-AWIPS

Mike Brennan, Chris Sisko and Wallace are making good progress on the N-AWIPS vertical cross section and vertical shear applications. These work with all of NHC’s primary models except NOGAPS. Mike said the NOGAPS problem is at NHC and is related to conversion from grib to GEMPAK format. Chris Sisko is developing some routines that used pre-specified levels. Wallace said that some type of wrapper may be needed before this is ready for general use.

Actions Needed:

a. Wallace will follow up to find out what is needed to get NOGAPS fields to be displayed.

b. Wallace will coordinate with the hurricane specialists when the application is ready for general testing.

8. HPLOT at NHC

The new HPLOT is running at NHC, with help from EMC and Ann. It is basically a grads-based GUI and can display many types of fields and model differences. It currently works with GFDL, HWRF and GFS. Additional grib files will be needed to display other models.

ADDITIONAL TOPICS

1. Mark is putting the ADD team call minutes at http://rammb.cira.colostate.edu/research/tropical_cyclones/hfip/add_conference_call_summaries.asp

2. The next call is scheduled for Wed, July 14, 2010 at 2 PM eastern. Ed will still be on leave, but Mark will lead the discussion. Wallace will call in with the leader code.

3. The HFIP ADD distribution list from the DTC site needs to be updated. Below is a proposed new list.

Actions Needed:

Provide comments on the distribution list

ADD Distribution List

Co-Leads:		 Ed Rappaport and Mark DeMaria

NHC: 			Wallace Hogsett, James Franklin, Chris Sisko, Richard Pasch

EMC:			Vijay Tallapragada, Janna O’Connor, Samuel Trahan, Zhan Zhang

NESDIS and CIRA: 	John Knaff, Kate Musgrave, Brian McNoldy

DTC and TCMC:		Barb Brown, Louisa Nance

ESRL:			Mike Fiorino, Tony Eckel, Zoltan Toth

NRL and SAIC:		Yi Jin, Buck Sampson, Ann Schrader

HRD: 			Gopal, Rob Rogers, Thiago Quirino

NWS:			Naomi Surgi

FSU:			T.N. Krishnamurti

HFIP:			Bob Gall