ADD Team Conference Call Minutes (Wed July 14, 2010, 2-3 PM EDT)

Attendees:  Mark DeMaria, Mike Fiorino, James Franklin, Wallace Hogsett, John Knaff, Yi Jin,  Brian McNoldy, Kate Musgrave, Louisa Nance, Janna O’Connor,  Richard Pasch, Buck Sampson, Chris Sisko, Bob Tuleya

AGENDA ITEMS

1. Status of Simulated Imagery

Simulate IR imagery from HWRF and GFS are now routinely being generated by EMC and displayed on the HWRF web page (http://www.emc.ncep.noaa.gov/gc_wmb/vxt/ ) using the color tables supplied by CIRA. This web page is no longer password protected. An upgrade to grads at EMC is still needed to properly display the colors.  Mark is generating plots of all four simulated GOES IR channels using McIDAS and also creating similar loops of real GOES data for a Hurricane Ike example. These will be posted on a web page at CIRA when completed.

Actions Needed:

a. Janna will let Mark know when grads at EMC is upgraded.

b. Mark will send a message to the NHC hurricane specialist list to request feedback on the EMC satellite images after the grads problem is fixed.

c. Mark will create the real and simulated imagery web page for the Hurricane Ike example.

2. Sample diagnostic file

Brian developed a simple ASCII diagnostic file and documentation.  He is routinely creating these in real time for HWRF and GFDL, which are posted at

http://einstein.atmos.colostate.edu/~mcnoldy/tropics/hwrf/2010

for HWRF with an analogous directory for GFDL.

Actions Needed:

a. Louisa will coordinate with Brian to develop a method for sending these files to DTC, where an archive will be saved. Other groups can follow that procedure if they begin to generate these files for other models.

3. Status of diagnostic file generation for global models and other regions models.

Mike is working on creating the ASCII diagnostic files for GFS, ECMWF, UkMet, Canadian, NOGAPS and FIM global models. He will compare results with Brian on a GFS test case. These should be ready soon. Mike will be visiting NRL to coordinate with Yi and Buck on the generation of the diagnostic files for COAMPS-TC and GFDN. The possibility of getting similar files from HWRFx still needs to be clarified.

Actions Needed:

a. Mark will contact HRD to identify an ADD focal point for future meetings (It might be Stan Goldenberg).

4. “Portable” version of SHIPS/LGEM

Kate is continuing development of a version of SHIPS/LGEM that can run off of the ASCII diagnostic files. She should have a preliminary version ready soon.

5. Other ensemble products

Mike is continuing development of ensemble based products, with emphasis on combining track and intensity information.

Actions Needed:

Mike will let the group know when he wants feedback on the ensemble products.

6. Vertical cross sections in N-AWIPS

N-AWIPS can now display vertical shear plots from most models. There is still a problem accessing NOGAPS. A GEMPAK procedure (outside of N-AWIPS) is also available for vertical cross-sections. When ready, Wallace will provide some training for NHC forecasters.

Actions Needed:

a. Chris and Richard will continue to follow up on the NOGAPS problem.

b. Wallace will provide some training to the NHC (probably by the end of July) on these applications.

7. HPLOT at NHC

The newest version of HPLOT is now installed and running at NHC.

Actions Needed:

a. Wallace will provide some training to the NHC (probably by the end of July) on these applications.

8. ADD Distribution List

Below is the proposed ADD distribution list. Mark will coordinate with Pam Johnson to change the hfip-ad@rap.ucar.edu accordingly.

Co-Leads:		 Ed Rappaport and Mark DeMaria

NHC: 			Wallace Hogsett, James Franklin, Chris Sisko, Richard Pasch

EMC:			Vijay Tallapragada, Janna O’Connor, Samuel Trahan, Zhan Zhang

NESDIS and CIRA: 	John Knaff, Kate Musgrave, Brian McNoldy

DTC and TCMC:		Barb Brown, Louisa Nance

ESRL:			Mike Fiorino,  Zoltan Toth

NRL and SAIC:		Yi Jin, Buck Sampson, Ann Schrader

GFDL:			Bob Tuleya

HRD: 			Stan Goldenberg, Gopal, Rob Rogers, Thiago Quirino

NWS:			Naomi Surgi

FSU:			T.N. Krishnamurti

HFIP:			Bob Gall

9. Next Call:

The next call is tentatively scheduled for Wed, July 28, 2010 at 2 PM eastern. Mark will be on travel, but Ed can lead the meeting if he is available.

Note: Past meeting minutes are available http://rammb.cira.colostate.edu/research/tropical_cyclones/hfip/add_conference_call_summaries.asp